## Sheet1
GAM403: Assessment 2 Milestones | Project: Dungeon Swarm | Developer: Matthew Allman
Milestone | Description | Due Date | Days Left | Completion Date | Notes
GAMEOBJECTS | Level Design | 2020-04-20 | 18
| Player and Weapons | 2020-04-23 | 21
| Enemies | 2020-04-26 | 24
| Pickups | 2020-04-24 | 22
| EXTRA - Decorative Objects (Barrels, Pillars, etc) |  |  |  | EXTRA ONLY
LIGHTING | Atmospheric Lighting | 2020-04-29 | 27 |  | Basic Lighting, (Advanced Lighting - EXTRA)
ANIMATION | Player/Enemy Animation | 2020-05-03 | 31
| Lighting Animation (Flickering Light, etc.) | 2020-05-06 | 34
| EXTRA - Weapon Attacks |  |  |  | EXTRA ONLY
| EXTRA - Door/Lever Animation |  |  |  | EXTRA ONLY
INPUT | Basic Movement Keys (WASD) Moving 2-Dimensional | 2020-04-03 | 1 | 2020-03-25 | Use Time.deltaTime to ensure movement is independent of Frame Rate. Use Input.GetAxis to simplify code.
| Mouse Buttons (Attack, Block) | 2020-04-10 | 8
| Pause Game (Esc) | 2020-04-03 | 1 | 2020-03-30 | Pausing the game goes to pause menu
| Change Weapons (NumPad, Number Buttons) | 2020-04-10 | 8 |  | Use WeaponSelect Task from Week 4 as a basis for the code
| Rotate Camera (Q and E) EXTRA |  |  |  | EXTRA ONLY - Holding down the button will rotate the camera on the Y Axis.
MOVEMENT | Character Movement - Translate, Rotate, Rigid Body | 2020-04-30 | 28 |  | Use AddForce, MovePosition and Velocity in FixedUpdate() for RigidBody
| Pickups - Rotation, Particle Effects on Pickup, Stat Adjustment | 2020-05-01 | 29 |  | Use RollerBall Exercise from Week 1
| Enemy Movement | 2020-05-03 | 31 |  | The Enemies need to lock on to the player and always be moving towards them. Enemies need to not collect pickups.
| Doors/Levers - EXTRA |  |  |  | EXTRA ONLY - Pulling Levers will open doors
INTERACTION | Attacks - Damage Enemy and Players when colliding with each other/with weapons | 2020-04-30 | 28 |  | Use Mesh Render only with low poly shapes *EXTRA TEXTURES
| Triggers | 2020-04-28 | 26 |  | If Pickups are collected,destroy the pickup and increase the corresponding skill
PROGRESS | Game Over Screen | 2020-05-01 | 29 |  | Display "GAME OVER", Time survived and final score when players health reaches 0
| UI - Health, Ammunition, Time, Score, Number of Enemies killed | 2020-04-30 | 28
| Difficulty Increase | 2020-05-06 | 34 |  | Stronger Enemies spawn after a certain Time has passed periodically
| EXTRA - Boss Spawn |  |  |  | EXTRA - When a certain number of enemies have been defeated, a boss will spawn
MISC EXTRAS - ONLY DO WHEN BASE GAME IS COMPLETED | Main Menu | 2020-04-03 | 1 | 2020-04-02 | Play and Exit Buttons
| Pause Menu | 2020-04-03 | 1 | 2020-03-30 | Resume, Menu, Quit Menu.
DEBUG/TEST GAME | Ensure Game is Working/No Major Bugs | 2020-05-07 | 35
BUILD SETTINGS | Create Settings and Build the Game | 2020-05-08 | 36
SUBMIT | Submit in Plato | 2020-05-09 | 37
Formulas:
Days Left = IF([Developer: Matthew Allman]<>"",[Developer: Matthew Allman]-TODAY(),"")